## Smoke Test Plan
Task | Completed by | Estimated Start | Estimated Completion | Scope/Remarks
Framework Redesign - Creation of Topcoder Testing Library - Usage of Wrappers for Protractor, Jasmine and Selenium in the lib, so that the actual app tests are completely independent | Sathya | Complete | 2020-04-24 | Community app:Login
Create wrappers in the Topcoder Testing Library for all major jasmine assertions and protractor element functions | Challenge 1 | 2020-04-28 | 2020-05-05 | Library Completion
Refactor the existing Community app smoke tests to use the new framework. Will include creation of page objects | Challenge 1 | 2020-05-09 | 2020-05-18 | Community app: Profile settings, tools, account, preferences, header,footer
| Challenge 2 | 2020-05-19 | 2020-05-30 | Community app: Challenge listing, Challenge details, member profile, dashboard
Challenge Listing
Challenge Details
Dashboard
Header
Footer
Profile Settings
Tools
Accounts
Preferences
Member Profile

## Header
Case Name | Case Number | Description | Preconditions | Test Data | Steps to Execute Test Case |  | Expected Result
[5 empty] | Steps Number | Steps
Before Login
To check Header links functionality | TC-001 | To verify that clicking topcoder logo directs user to topcoder home page (business) | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on the topcoder logo in the Header. | User is directed to topcoder home page (business).
| TC-002 | To verify that clicking Business link directs user to topcoder home page (business) | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on the Business link in the Header. | User is directed to topcoder home page (business).
To check Community menu functionality | TC-003 | To verify that Community menu displays the following submenus: Overview, How It Works | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click the Community menu subpage. | Community menu displays the following submenus: Overview, How It Works
| TC-004 | To verify that clicking How It Works submenu directs user to Thrive Page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Community menu | Community menu is highlighted in green
[5 empty] | 3 | Click on the How It Works submenu Community menu subpage. | User is directed to Thrive Page.
| TC-005 | To verify that clicking Overview submenu directs user to Overview/Learn page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Community menu | Community menu is highlighted in green
[5 empty] | 3 | Click on the Overview submenu in Community menu subpage. | User is directed Overview/Learn page.
To check Compete menu functionality | TC-006 | To verify that Compete menu displays the following submenus: All Challenges, Competitive Programming and Gig work | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Compete Menu. | Compete menu displays the following submenus: All Challenges, Competitive Programming and Gig work.
| TC-007 | To verify that clicking All Challenges submenu directs user to challenge listing page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Compete Menu. | Compete menu displays the following submenus: All Challenges, Competitive Programming and Gig work.
[5 empty] | 3 | Click on All Challenges submenu. | User is directed to challenge listing page
| TC-008 | To verify that clicking Gig work submenu directs user to taas page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Compete Menu. | Compete menu displays the following submenus: All Challenges, Competitive Programming and Gig work.
[5 empty] | 3 | Click on Gig work submenu. | User is directed to taas page page.
| TC-009 | To verify that clicking Competitive Programming submenu directs user to login page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Compete Menu. | Compete menu displays the following submenus: All Challenges, Competitive Programming and Gig work.
[5 empty] | 3 | Click on Competitive Programming submenu. | User is directed to login page.
To check Tracks menu functionality | TC-010 | To verify that Tracks menu displays the following submenus: Competitive Programming, Data Science, Design, Development, QA | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Tracks Menu. | Tracks menu displays the following submenus: Competitive Programming, Data Science, Design, Development, QA
| TC-011 | To verify that clicking Competitive Programming submenu directs user to thrive's competitive programming page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Tracks Menu. | Tracks menu is highlighted in green
[5 empty] | 3 | Click on Competitive Programming submenu. | User is directed to thrive's competitive programming page.
| TC-012 | To verify that clicking Data Science submenu directs user to thrive's Data Science page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Tracks Menu. | Tracks menu is highlighted in green
[5 empty] | 3 | Click on Data Science submenu. | User is directed to thrive's Data Science page.
| TC-013 | To verify that clicking Design submenu directs user to thrive's Design page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Tracks Menu. | Tracks menu is highlighted in green
[5 empty] | 3 | Click on Design submenu. | User is directed to thrive's Design page.
| TC-014 | To verify that clicking Development submenu directs user to thrive's Development page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Tracks Menu. | Tracks menu is highlighted in green
[5 empty] | 3 | Click on Development submenu. | User is directed to thrive's Development page.
| TC-015 | To verify that clicking QA submenu directs user to thrive's QA page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Tracks Menu. | Tracks menu is highlighted in green
[5 empty] | 3 | Click on QA submenu. | User is directed to thrive's QA page.
To check Explore menu functionality | TC-016 | To verify that Explore menu displays the following submenus: TCO, Programs, Forums, Statistics, Blog, Thrive | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Explore Menu. | Explore menu displays the following submenus: TCO, Programs, Forums, Statistics, Blog, Thrive
| TC-017 | To verify that clicking TCO submenu directs user to Topcoder Open page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Explore Menu. | Explore menu is highlighted in green
[5 empty] | 3 | Click on TCO submenu. | User is directed to Topcoder Open page.
| TC-018 | To verify that clicking Programs submenu directs user to Member Programs page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Explore Menu. | Explore menu is highlighted in green
[5 empty] | 3 | Click on Programs submenu. | User is directed to Member Programs page.
| TC-019 | To verify that clicking Forums submenu directs user to forums page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Explore Menu. | Explore menu is highlighted in green
[5 empty] | 3 | Click on Forums submenu. | User is directed to forums page.
| TC-018 | To verify that clicking Statistics submenu directs user to Statistics page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Explore Menu. | Explore menu is highlighted in green
[5 empty] | 3 | Click on Statistics submenu. | User is directed to Statistics page.
| TC-019 | To verify that clicking Blog submenu directs user to Blog page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Explore Menu. | Explore menu is highlighted in green
[5 empty] | 3 | Click on Blog submenu. | User is directed to Blog page.
| TC-020 | To verify that clicking Thrive submenu directs user to Thrive page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Explore Menu. | Explore menu is highlighted in green
[5 empty] | 3 | Click on Thrive submenu. | User is directed to Thrive page.
To check Login button functionality | TC-021 | To verify that clicking Login button directs user to Login page | User is not logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Observe the Header. | User can see Login button menu in the Header.
[5 empty] | 3 | Click on Login button. | User is directed to Login page.
After Login
To check Header links functionality | TC-022 | To verify that clicking topcoder logo directs user to dashboard page (business) | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on the topcoder logo in the Header. | User is directed to the dashboard page
| TC-023 | To verify that clicking Business link directs user to topcoder home page (business) | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on the Business link in the Header. | User is directed to topcoder home page (business).
To check Community menu functionality | TC-024 | To verify that Community menu displays the following submenus: Dashboard, My Profile, Payments | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Community page
[5 empty] | 2 | Click on Community menu | Community menu displays the following submenus: Dashboard, My Profile, Payments
| TC-025 | To verify that clicking My Profile submenu directs user to My Profile page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Community page
[6 empty] | Click on Community menu. | Community menu turns green.
[5 empty] | 2 | Click on My Profile submenu. | User is directed to My Profile page.
| TC-026 | To verify that clicking Payments submenu directs user to Payments page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Community page
[6 empty] | Click on Community menu. | Community menu turns green.
[5 empty] | 2 | Click on Payments submenu. | User is directed to Payments page.
| TC-027 | To verify that clicking Dashboard submenu directs user to Dashboard page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Community page
[6 empty] | Click on Community menu. | Community menu turns green.
[5 empty] | 2 | Click on Dashboard submenu. | User is directed to Dashboard page.
To check Compete menu functionality | TC-028 | To verify that Compete menu displays the following submenus: All Challenges, Competitive Programming and Gig work | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Compete Menu. | Compete menu displays the following submenus: All Challenges, Competitive Programming and Gig work.
| TC-029 | To verify that clicking All Challenges submenu directs user to challenge listing page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Compete Menu. | Compete menu displays the following submenus: All Challenges, Competitive Programming and Gig work.
[5 empty] | 3 | Click on All Challenges submenu. | User is directed to challenge listing page
| TC-030 | To verify that clicking Gig work submenu directs user to taas page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Compete Menu. | Compete menu displays the following submenus: All Challenges, Competitive Programming and Gig work.
[5 empty] | 3 | Click on Gig work submenu. | User is directed to taas page page.
| TC-031 | To verify that clicking Competitive Programming submenu directs user to topcoder arena page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Community page
[5 empty] | 2 | Click on Compete Menu. | Compete menu displays the following submenus: All Challenges, Competitive Programming and Gig work.
[5 empty] | 3 | Click on Competitive Programming submenu. | User is directed to topcoder arena page page.
To check Tracks menu functionality | TC-032 | To verify that Tracks menu displays the following submenus: Competitive Programming, Data Science, Design, Development, QA | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Tracks Menu. | Tracks menu displays the following submenus: Competitive Programming, Data Science, Design, Development, QA
| TC-033 | To verify that clicking Competitive Programming submenu directs user to thrive's competitive programming page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Tracks Menu. | Tracks menu is highlighted in green
[5 empty] | 3 | Click on Competitive Programming submenu. | User is directed to thrive's competitive programming page.
| TC-034 | To verify that clicking Data Science submenu directs user to thrive's Data Science page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Tracks Menu. | Tracks menu is highlighted in green
[5 empty] | 3 | Click on Data Science submenu. | User is directed to thrive's Data Science page.
| TC-035 | To verify that clicking Design submenu directs user to thrive's Design page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Tracks Menu. | Tracks menu is highlighted in green
[5 empty] | 3 | Click on Design submenu. | User is directed to thrive's Design page.
| TC-036 | To verify that clicking Development submenu directs user to thrive's Development page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Tracks Menu. | Tracks menu is highlighted in green
[5 empty] | 3 | Click on Development submenu. | User is directed to thrive's Development page.
| TC-037 | To verify that clicking QA submenu directs user to thrive's QA page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Tracks Menu. | Tracks menu is highlighted in green
[5 empty] | 3 | Click on QA submenu. | User is directed to thrive's QA page.
To check Explore menu functionality | TC-038 | To verify that Explore menu displays the following submenus: TCO, Programs, Forums, Statistics, Blog, Thrive | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Explore Menu. | Explore menu displays the following submenus: TCO, Programs, Forums, Statistics, Blog, Thrive
| TC-039 | To verify that clicking TCO submenu directs user to Topcoder Open page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Explore Menu. | Explore menu is highlighted in green
[5 empty] | 3 | Click on TCO submenu. | User is directed to Topcoder Open page.
| TC-040 | To verify that clicking Programs submenu directs user to Member Programs page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Explore Menu. | Explore menu is highlighted in green
[5 empty] | 3 | Click on Programs submenu. | User is directed to Member Programs page.
| TC-041 | To verify that clicking Forums submenu directs user to forums page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Community page
[5 empty] | 2 | Click on Explore Menu. | Explore menu is highlighted in green
[5 empty] | 3 | Click on Forums submenu. | User is directed to forums page.
| TC-042 | To verify that clicking Statistics submenu directs user to Statistics page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Explore Menu. | Explore menu is highlighted in green
[5 empty] | 3 | Click on Statistics submenu. | User is directed to Statistics page.
| TC-043 | To verify that clicking Blog submenu directs user to Blog page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Explore Menu. | Explore menu is highlighted in green
[5 empty] | 3 | Click on Blog submenu. | User is directed to Blog page.
| TC-044 | To verify that clicking Thrive submenu directs user to Thrive page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Explore Menu. | Explore menu is highlighted in green
[5 empty] | 3 | Click on Thrive submenu. | User is directed to Thrive page.
To check Notifications functionality | TC-045 | To verify that Bell icon opens the notifications popup | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Bell icon. | Notifictaions Popup is displayed
| TC-046 | To verify that View All Notifictaions Link opens the Notifications page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Challenge Listing page
[5 empty] | 2 | Click on Bell icon. | Notifictaions Popup is displayed
[5 empty] | 3 | Click on View All Notifications link | User should land on Notifications page
To check User menu Clickable items functionality | TC-047 | To verify that clicking inside the user info section (where the avatar, handle, and email is displayed) directs user to profile page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Community page
[5 empty] | 2 | Click on user handle. | User can see the user menu opens.
[5 empty] | 3 | Click inside the user info section. | User Is directed to profile page.
| TC-048 | To verify that clicking Switch To Business link directs user to topcoder home page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Community page
[5 empty] | 2 | Click on user handle. | User can see the user menu opens.
[5 empty] | 3 | Click Switch To Business link. | User Is directed to topcoder home page.
| TC-049 | To verify that clicking Settings link directs user to settings page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Community page
[5 empty] | 2 | Click on user handle. | User can see the user menu opens.
[5 empty] | 3 | Click Settings link. | User Is directed to settings page.
| TC-050 | To verify that clicking Help link directs user to help page | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Community page
[5 empty] | 2 | Click on user handle. | User can see the user menu opens.
[5 empty] | 3 | Click Help link. | User Is directed to Help page.
| TC-051 | To verify that clicking Logout button logouts the user from topcoder | User is logged in |  | 1 | Go to "https://www.topcoder.com/challenges" | User should land on Topcoder Community page
[5 empty] | 2 | Click on user handle. | User can see the user menu opens.
[5 empty] | 3 | Click Logout button. | User Is logged out from topcoder

## Footer
Case Name | Case Number | Description | Preconditions | Test Data | Steps to Execute Test Case |  | Expected Result | Actual Result | Status
[5 empty] | Steps Number | Steps
To verify the content of the Footer below the page displayed. | TC-001 | To verify the Footer contains different headers. | User is in the challenge listing page. |  | 1 | Observe the headers displayed in the Footer. | Should display Compete, Tracks, Community, Help Center, About and Follow Us headers in the footer.
|  | To verify the Compete headers contains different links. | User is in the challenge listing page. |  | 1 | Observe the different links displayed under Compete header. | Should display "All Challenges", "Competitive Programming" and "gig Work" links.
|  | To verify the Tracks headers contains different links. | User is in the challenge listing page. |  | 1 | Observe the different links displayed under Tracks header. | Should display "Competitive Programming", "Data Science", "Design", "Development" and "QA" links.
|  | To verify the Community headers contains different links. | User is in the challenge listing page. |  | 1 | Observe the different links displayed under Community header. | Should display "TCO", "Programs", "Forums", "Statistics", "Blog" and "Thrive" links.
|  | To verify the Help Center headers contains different links. | User is in the challenge listing page. |  | 1 | Observe the different links displayed under Help Center header. | Should display "Getting Paid", "FAQ", "General Info" and "Website Help".
|  | To verify the About Us headers contains different links. | User is in the challenge listing page. |  | 1 | Observe the different links displayed under About Us header. | Should display "Admins", "Contact Us", "Join Community", "About Community", "Changelog" and "Talk to Sales" links
|  | To verify the Follow Us headers contains different links. | User is in the challenge listing page. |  | 1 | Observe the different links displayed under Follow Us header. | Should display Facebook, Youtube, LinkedIn, Twitter and Instagram icons.
To verify that the links under Compete are working from the Footer. | TC-002 | To verify clicking on All challenges displays challenge listing page. | User is in the challenge listing page. |  | 1 | Click on the "All Challenges" link from the Footer. | User should be redirected to the challenge listing page.
|  | To verify clicking on Competitive Programming redirects to arena page. | 1. User is logged in. 2. User is in the challenge listing page. |  | 1 | Click on the "Competitive Programming" link. | User should get redirected to Arena page
|  | To verify clicking on Competitive Programming redirects to login page. | 1. User is not logged in. 2. User is in the challenge listing page. |  | 1 | Click on the "Competitive Programming" link. | User should get redirected to topcoder login page.
|  | To verify clicking on Gig Work redirects to gig work page. | User is in the challenge listing page. |  | 1 | Click on "Gig Work" link. | User should be redirected to gid work page.
To verify that the links under Tracks are working from the Footer. | TC-003 | To verify clicking on the Competitive Programming redirects to Thrive's Competitive Programming. | User is in the challenge listing page. |  | 1 | Click Competitive Programming | User should get redirected to Thrive's Competitive Programming page.
|  | To verify clicking on the Data Science redirects to thrive's data science page. | User is in the challenge listing page. |  | 1 | Click Data Science | User should get redirected to Thrive's Data Science home page
|  | To verify clicking on the Design redirects to Thrive's design home page. | User is in the challenge listing page. |  | 1 | Click Design | User should get redirected to Thrive's Design home page
|  | To verify clicking on the Development redirects to Thrive's development home page. | User is in the challenge listing page. |  | 1 | Click Development | User should get redirected to Thrive's Development home page
|  | To verify clicking on the QA redirects to Thrive's QA homepage. | User is in the challenge listing page. |  | 1 | Click QA | User should get redirected to Thrive's QA home page
To verify that the links under Community are working from the header. | TC-004 | To verify clicking on TCO redirects to TCO page. | User is in the challenge listing page. |  | 1 | Click TCO | User should get redirected to TCO page
|  | To verify clicking on Program redirects to Members program page. | User is in the challenge listing page. |  | 1 | Click Programs | User should get redirected to Member Programs page
|  | To verify clicking on Forums redirects to forums page. | 1. User should be logged in 2. User is in the challenge listing page. |  | 1 | Click on Forums. | User should be redirected to topcoder login page when the user is not logged in.
|  | To verify clicking on Forums redirects to login page | 1. User is not logged in. 2. User is in the challenge listing page. |  | 1 | Click on Forums. | User should be redirected to topcoder login page when the user is not logged in.
|  | To verify clicking on Statistics redirects to statistics page. | User is in the challenge listing page. |  | 1 | Click Statistics | User should get redirected to Statistics page
|  | To verify clicking on Blog redirects to Topcoder Blog page. | User is in the challenge listing page. |  | 1 | Click Blog | User should get redirected to Blog page
|  | To verify clicking on Thrive redirects to Thrive page. | User is in the challenge listing page. |  | 1 | Click Thrive | User should get redirected to Thrive page
To verify that the links under Help Center are working from the header. | TC-005 | To verify clicking on the Getting Paid link redirects to getting paid information page. | User is in the challenge listing page. |  | 1 | Click on Getting Paid. | User should be redirected to Getting Paid information page.
|  | To verify clicking on FAQ redirects to FAQ page. | User is in the challenge listing page. |  | 1 | Click on FAQ link. | User should be redirected to FAQ page.
|  | To verify clicking on General Info link redirects to topcoder information page. | User is in the challenge listing page. |  | 1 | Click on General Info. | User should be redirected to topcoder information page.
|  | To verify clicking on Website Help link opens an email app. | User is in the challenge listing page. |  | 1 | Click on Website Help. | Clicking Website Help should prompt the user to open an email app
To verify that the links under About are working from the footer. | TC-006 | To verify clicking on Admins redirects to community team admins page. | User is in the challenge listing page. |  | 1 | Click on Admins link. | User should be redirected to community team admins page.
|  | To verify clicking on Contact Us redirects to topcoder contact page. | User is in the challenge listing page. |  | 1 | Click on the Contact Us link displayed. | User should be redirected to Topcoder Contact page.
|  | To verify clicking on Join Community redirects to registration page. | User is in the challenge listing page. |  | 1 | Click on Join Community link. | User should be redirected to Topcoder registration page.
|  | To verify clicking on About Community redirects to community page. | User is in the challenge listing page. |  | 1 | Click on About Community link. | User should be redirected to Topcoder community page.
|  | To verify clickign on Changelog displays community website changelog page. | User is in the challenge listing page. |  | 1 | Click on Changelog. | User should redirected to Community Website changelog page.
|  | To verify clicking on Talk to Sales redirects to contact page. | User is in the challenge listing page. |  | 1 | Click on Talk to Sales link. | User should be redirected to contact page.
To verify Footer social icons functionality | TC-007 | To verify that clicking Facebook icon directs user to Topcoder Facebook page | User is in the challenge listing page. |  | 1 | Click on Facebook icon in the footer. | User is redirected to Topcoder Facebook page.
|  | To verify that clicking Twitter icon directs user to Topcoder Twitter page | User is in the challenge listing page. |  | 1 | Click on Twitter icon in the footer. | User is redirected to Topcoder Twitter page.
|  | To verify that clicking Linkedin icon directs user to Topcoder Linkedin page | User is in the challenge listing page. |  | 1 | Click on Linkedin icon in the footer. | User is redirected to Topcoder Linkedin page.
|  | To verify that clicking Instagram icon directs user to Topcoder Instagram page | User is in the challenge listing page. |  | 1 | Click on Instagram icon in the footer. | User is redirected to Topcoder Instagram page.
To verify Policies link is present. | TC-008 | To verify Policies link is present beside the copyright info. | User is in the challenge listing page. |  | 1 | Observe the Policies link present beside the copyright info. | Policies link should be present beside the copyright info.
To verify the functionality of Policies link | TC-009 | To verify clicking on the Policies link redirects to privacy policy page. | User is in the challenge listing page. |  | 1 | Click on the Policies link. | User should be redirected to Privacy Policy page.

## Profile Settings
Case Name | Case Number | Description | Preconditions | Test Data | Steps to Execute Test Case |  | Expected Result
[5 empty] | Steps Number | Steps
Basic Info | TC_001 | To verify whether the current user can update basic information. | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/settings/profile"
[5 empty] | 2 | Update the user information like i. Personal Details( First Name, Last name, Birth Date, Address, Address 2, City, State, Zip, Country), ii. About you (Gender, T-shirt Size, Current Location, Primary Interest, Short Bio) and iii. Track (Design , Development And Data Science )
[5 empty] | 3 | Click on Save Changes | User should get the update success message with "Your information has been updated."
[5 empty] | 4 | Go to the given URL " https://www.topcoder.com/settings/profile" | System should show the information which was updated on step 2. Note :For verification you can show 2 or 3 fields eg First Name, Last name and Country.
Language | TC_002 | Verify User can Add/Update/Delete language | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/settings/profile"
[5 empty] | 2 | Click on Language menu at Left menu Section
[5 empty] | 3 | Select language, Spoken Level and Written Level
[5 empty] | 4 | Click on "Add language to your list " button | 1. User should get the message "Your information has been updated." 2. New added language should display on Your language section.
[5 empty] | 5 | Click on Edit button at recently added language
[5 empty] | 6 | Update any filed (Language, Spoken Level, Written Level)
[5 empty] | 7 | Click on "Edit Language to your list" button. | 1. User should get the message "Your information has been updated." 2. Updated value should reflect on language list section.
[5 empty] | 8 | Click on Delete button at recently updated language. | User should get the confirmation window to delete the language.
[5 empty] | 9 | Click on "Yes, Delete" button | 1. Selected language should be deleted from the list. 2. User should get the message "Your information has been updated."
Education | TC_003 | Verify User can Add/Update/Delete Education | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/settings/profile"
[5 empty] | 2 | Click on Education link at Left menu Section
[5 empty] | 3 | Input the fields like Name of College or University, Major, Start Date, End Date and Graduated.
[5 empty] | 4 | Click on "Add education to your list " button | 1. User should get the message "Your information has been updated." 2. New added education details should display on Your education section.
[5 empty] | 5 | Click on Edit button at recently added education.
[5 empty] | 6 | Update any filed ( eg. Name of college)
[5 empty] | 7 | Click on "Edit education to your list" button. | 1. User should get the message "Your information has been updated." 2. Updated value should reflect on education list section.
[5 empty] | 8 | Click on Delete button at recently updated education. | User should get the confirmation window to delete the education.
[5 empty] | 9 | Click on "Yes, Delete" button | 1. Selected education should be deleted from the list. 2. User should get the message "Your information has been updated."
Work | TC_004 | Verify User can Add/Update/Delete work | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/settings/profile"
[5 empty] | 2 | Click on work link at Left menu Section
[5 empty] | 3 | Input the fields like Company, Position, Industry, City, Start Date , End Date and I am currently Working in this role.
[5 empty] | 4 | Click on "Add workplace to your list " button | 1. User should get the message "Your information has been updated." 2. New added workplace details should display on your workplaces section.
[5 empty] | 5 | Click on Edit button at recently added workplace.
[5 empty] | 6 | Update any filed ( eg. Company)
[5 empty] | 7 | Click on "Edit workplace to your list" button. | 1. User should get the message "Your information has been updated." 2. Updated value should reflect on workplace list section.
[5 empty] | 8 | Click on Delete button at recently updated education. | User should get the confirmation window to delete the workplace.
[5 empty] | 9 | Click on "Yes, Delete" button | 1. Selected workplace should be deleted from the list. 2. User should get the message "Your information has been updated."
Skills | TC_005 | Verify User can Add/Delete skill. | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/settings/profile"
[5 empty] | 2 | Click on skills link at Left menu Section
[5 empty] | 3 | Select any new skill from skills drop down.
[5 empty] | 4 | Click on "Add Skill to your list" | 1. User should get the message "Success! Skill "*****" i..e selected skill was added" 2. New added skill should reflect on your skills list section.
[5 empty] | 5 | Click on recently added skill. | User should get the confirmation window to delete the skill.
[5 empty] | 6 | Click on "Yes, Delete" button | 1. Selected skill should be deleted from the list. 2. User should get the message "Skill "***" was removed." i.e. selected skill
Hobbies | TC_006 | Verify User can Add/Update/Delete the hobby. | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/settings/profile"
[5 empty] | 2 | Click on Hobbies link at Left menu Section
[5 empty] | 3 | Input the fields Hobby and Description at Add a new hobby section.
[5 empty] | 4 | Click on "Add hobby to your list " button | 1. User should get the message "Your information has been updated." 2. New added hobby details should display on your hobbies section.
[5 empty] | 5 | Click on Edit button at recently added hobby.
[5 empty] | 6 | Update any filed ( eg. hobby)
[5 empty] | 7 | Click on "Edit hobby to your list" button. | 1. User should get the message "Your information has been updated." 2. Updated value should reflect on your hobbies list section.
[5 empty] | 8 | Click on Delete button at recently updated hobby. | User should get the confirmation window to delete the hobby.
[5 empty] | 9 | Click on "Yes, Delete" button | 1. Selected hobby should be deleted from the list. 2. User should get the message "Your information has been updated."
Communities | TC_007 | Verify User can update the community. | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/settings/profile"
[5 empty] | 2 | Click on Communities link at Left menu Section
[5 empty] | 3 | Click the radio button at "Topcoder Blockchain Community" | 1. . User should get the message "Your information has been updated."

## Tools
Case Name | Case Number | Description | Preconditions | Test Data | Steps to Execute Test Case |  | Expected Result | Actual Result | Status
[5 empty] | Steps Number | Steps
Devices | TC_001 | Verify User can Add/Update/Delete Device | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/settings/tools"
[5 empty] | 2 | Click on Devices menu at Left menu Section
[5 empty] | 3 | Input the fields Type, Manufacturer, Model, OS, OS Version, OS Language at Add a new device section
[5 empty] | 4 | Click on "Add device to your list " button | 1. User should get the message "Your information has been updated." 2. New added device should display on Your language section.
[5 empty] | 5 | Click on Edit button at recently added Device
[5 empty] | 6 | Update any filed (eg Device Type )
[5 empty] | 7 | Click on "Edit Device to your list" button. | 1. User should get the message "Your information has been updated." 2. Updated value should reflect on your device list section.
[5 empty] | 8 | Click on Delete button at recently updated language. | User should get the confirmation window to delete the device.
[5 empty] | 9 | Click on "Yes, Delete" button | 1. Selected device should be deleted from the list. 2. User should get the message "Your information has been updated."
Software | TC_002 | Verify User can Add/Update/Delete Software | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/settings/tools"
[5 empty] | 2 | Click on Software menu at Left menu Section
[5 empty] | 3 | Input the fields Type and Name at Add a new software section
[5 empty] | 4 | Click on "Add software to your list " button | 1. User should get the message "Your information has been updated." 2. New added software should display on Your software section.
[5 empty] | 5 | Click on Edit button at recently added Software
[5 empty] | 6 | Update any filed (eg Type or Name )
[5 empty] | 7 | Click on "Edit software to your list" button. | 1. User should get the message "Your information has been updated." 2. Updated value should reflect on your device list section.
[5 empty] | 8 | Click on Delete button at recently updated software. | User should get the confirmation window to delete the device.
[5 empty] | 9 | Click on "Yes, Delete" button | 1. Selected software should be deleted from the list. 2. User should get the message "Your information has been updated."
Service Providers | TC_003 | Verify User can Add/Update/Delete Service Provider | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/settings/tools"
[5 empty] | 2 | Click on Service Providers link at Left menu Section
[5 empty] | 3 | Input the fields Name and Type at Add a new Service Provider sectction.
[5 empty] | 4 | Click on "Add Service Provider to your list " button | 1. User should get the message "Your information has been updated." 2. New added Service Provider should display on Your Service Providers section.
[5 empty] | 5 | Click on Edit button at recently added Service Provider
[5 empty] | 6 | Update any filed (eg Type or Name )
[5 empty] | 7 | Click on "Edit software to your list" button. | 1. User should get the message "Your information has been updated." 2. Updated value should refelect on your Service Provider list section.
[5 empty] | 8 | Click on Delete button at recently updated software. | User should get the confirmation window to delete the Service Provider.
[5 empty] | 9 | Click on "Yes, Delete" button | 1. Selected Service Provider should be deleted from the list. 2. User should get the message "Your information has been updated."
Subscriptions | TC_004 | Verify User can Add/Update/Delete Subscriptions | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/settings/tools"
[5 empty] | 2 | Click on Subscriptions link at Left menu Section
[5 empty] | 3 | Input the field Name at Add a new Subscriptions section
[5 empty] | 4 | Click on "Add Subscriptions to your list " button | 1. User should get the message "Your information has been updated." 2. New added subscriptions should display on Your subscriptions section.
[5 empty] | 5 | Click on Edit button at recently added subscription
[5 empty] | 6 | Update Name Filed.
[5 empty] | 7 | Click on "Edit software to your list" button. | 1. User should get the message "Your information has been updated." 2. Updated value should reflect on your subscription list section.
[5 empty] | 8 | Click on Delete button at recently updated software. | User should get the confirmation window to delete the Service Provider.
[5 empty] | 9 | Click on "Yes, Delete" button | 1. Selected subscription should be deleted from the list. 2. User should get the message "Your information has been updated."

## Account
Case Name | Case Number | Description | Preconditions | Test Data | Steps to Execute Test Case |  | Expected Result
[5 empty] | Steps Number | Steps
My Account | TC_001 | Verify User can update his/her User Consent. | User should be logged in. |  | 1 | Go to the given URL "https://www.topcoder.com/settings/account"
[5 empty] | 2 | Update User Consent under end of Account Section. Activate the toggle button. | User should get the message "Your information has been updated.
Linked Accounts | TC_002 | Verify User can Add/Delete External Link. | User should be logged in. |  | 1 | Go to the given URL "https://www.topcoder.com/settings/account"
[5 empty] | 2 | Click on Linked Account link at Left menu Section
[5 empty] | 3 | Input external link at Add a new external link section.
[5 empty] | 4 | Click on "Add Link" button | User should get the message "Your link has been added. Data from your link will be visible on your profile shortly".
[5 empty] | 5 | Click on Delete button at recently added link. | User should get the confirmation window to delete the device.
[5 empty] | 6 | Click on "Yes, Delete" button | 1. Selected link should be deleted from the list. 2. User should get the message "Your web link "*****" was removed.."
Note :Change email/password/Linked accounts is out of scope.

## Preferences
Case Name | Case Number | Description | Preconditions | Test Data | Steps to Execute Test Case |  | Expected Result
[5 empty] | Steps Number | Steps
Email | TC_001 | Placeholder | Placeholder |  | Placeholder | Placeholder
Forum | TC_002 | Verify User can redirect to forums's setting page | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/settings/preferences"
[5 empty] | 2 | Click on Forum link at Left menu Section | User Should redirect to https://apps.topcoder.com/forums/?module=Settings
Payment | TC_003 | Verify User can redirect to Payment details page | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/settings/preferences"
[5 empty] | 2 | Click on Payment link at Left menu Section | User Should redirect to https://community.topcoder.com/PactsMemberServlet?module=PaymentHistory&full_list=false
Note :Email preferences is not in scope for now

## Challenge Listings
Case Name | Case Number | Description | Preconditions | Test Data | Steps to Execute Test Case |  | Expected Result | Actual Result | Status
[5 empty] | Steps Number | Steps
Before Login Test Cases
Join button verification (Before Login) | TC_001 | To verify whether the current page is redirected to Registration page on clicking the Join button | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the Join button into top right corner. | User should be redirected to the registration page.
Login button verification (Before Login) | TC_002 | To verify whether the current page is redirected to Login page on clicking the Log in button. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the Log in button into top right corner. | User should be redirected to the login page.
Member Search Function (Before Login) | TC_003 | To verify whether the user is able to search the member by their username/skill using the search icon. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the search icon into top right corner. | Find members textbox should be opened.
[5 empty] | 3 | Type a valid username and click search icon into textbox. | Members with the entered username should be listed. | please refer this thread for more info : https://apps.topcoder.com/forums/?module=Thread&threadID=946206&start=0&mc=2#2373587
[5 empty] | 4 | Type a valid skill and click search icon into textbox. | Members with the entered skill should be listed.
Challenge tab (Before Login) | TC_004 | To verify whether all the open for registration and Ongoing challenges are listed on clicking the Challenge tab. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the Challenge tab. | All the open for registration and Ongoing challenges should be listed.
SRM tab (Before Login) | TC_005 | To verify whether login page is opened on clicking the SRM tab. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the SRM tab. | Login page should be opened into new tab of the browser.
Search Challenges Textbox (Before Login) | TC_006 | To verify whether the user is able to search for a challenge by using the Search challenges textbox. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Enter a valid challenge name into Search challenge textbox and click the search icon. | The particular challenge entered should be displayed into Challenge listing page.
FIlter drop down (Before login) | TC-007 | To verify that the 'Filter' button is working correctly | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listings page
[5 empty] | 2 | Select the "Filter' button on the left side of page | The filter drop down should appear
Keyword Filter (Before login) | TC-008 | To verify that the 'Filter' option 'keywords' is working correctly | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listings page
[5 empty] | 2 | Select the "Filter' button on the left side of page | The filter drop down should appear
[5 empty] | 3 | Go to the 'keywords' field and select a keyword | Only challenges that include the selected keyword should appear
Subtrack Filter (Before login) | TC-009 | To verify that the 'Filter' option 'Subtrack' is working correctly | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listings page
[5 empty] | 2 | Select the "Filter' button on the left side of page | The filter drop down should appear
[5 empty] | 3 | Go to the 'Subtrack' field and select a subtrack | Only challenges that include the selected subtrack should appear
Sub Community filter (Before login) | TC-010 | To verify that the 'Filter' option 'Sub Community' is working correctly | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listings page
[5 empty] | 2 | Select the "Filter' button on the left side of page | The filter drop down should appear
[5 empty] | 3 | Go to the 'Sub Community' field and select a sub community | Only challenges into selected Sub community should appear
Date range filter (Before login) | TC-011 | To verify that the 'Filter' option for 'Date range' is workingcorrectly | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listings page
[5 empty] | 2 | Select the "Filter' button on the left side of page | The filter drop down should appear
[5 empty] | 3 | Go to the 'date range' fields and enter a start and end date | Only challenges into selected date range should appear
Filter function - all filters applied (Before Login) | TC_012 | To verify whether the challenges are filtered according to the keyword/Subtrack/Sub community/Date range fields selected under the Filter function. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the Filter button. | The dropdowns for the filter criteria Keyword,Subtrack,Sub Community and Date range should be displayed.
[5 empty] | 3 | Select the filters under the criteria Keyword,Subtrack,Sub Community and Date range. | The challenges listed should be filtered according to the selected criteria.
More than one Keywords and Subtracks(Before Login) | TC_013 | To verify whether the user is able to select more than one keyword/Subtrack under the filter function. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the Filter button. | The dropdowns for the filter criteria Keyword,Subtrack,Sub Community and Date range should be displayed.
[5 empty] | 3 | Select more than one Keyword/Subtrack. | The user should be able to select more than one keyword/Subtrack.
Deselection of keywords and subtracks (Before Login) | TC_014 | To verify whether the cross symbol inside the textbox keyword/Subtrack filters removes the selected keyword/Subtrack. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the Filter button. | The dropdowns for the filter criteria Keyword,Subtrack,Sub Community and Date range should be displayed.
[5 empty] | 3 | Select more than one Keyword/Subtrack. | The user should be able to select more than one keyword/Subtrack.
[5 empty] | 4 | Click the cross symbol inside the textbox of Keyword/Subtrack. | The selected filters should be removed.
Number of filters applied (Before Login) | TC_015 | To verify whether the number of filters applied are shown into Filter button according to the keyword/Subtrack/Sub community/Date range fields selected. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the Filter button. | The dropdowns for the filter criteria Keyword,Subtrack,Sub Community and Date range should be displayed.
[5 empty] | 3 | Select the filters under the criteria Keyword,Subtrack,Sub Community and Date range. | The number of filters applied should be shown into Filters button.
Clear button (Before Login) | TC_016 | To verify whether the clear filter button clears all the filters selected and all the challenges are displayed. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the Filter button. | The dropdowns for the filter criteria Keyword,Subtrack,Sub Community and Date range should be displayed.
[5 empty] | 3 | Select the filters under the criteria Keyword,Subtrack,Sub Community and Date range. | The challenges listed should be filtered according to the selected criteria.
[5 empty] | 4 | Click Clear Filter button. | The clear filter button should clear all the filters selected and all the challenges should be listed.
Save button (Before Login) | TC_017 | To verify whether the Save filter button is deactivated into filter function. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the Filter button. | The dropdowns for the filter criteria Keyword,Subtrack,Sub Community and Date range should be displayed.
[5 empty] | 3 | Select the filters under the criteria Keyword,Subtrack,Sub Community and Date range. | The Save filter button should be in deactivated state.
Sort by (Before Login) | TC_018 | To verify whether the Sort by select option under the Open for registration/Ongoing Challenges list sorts the challenges according to the selected option. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Select an option from the Sort by dropdown list into Open for registration/Ongoing challenges list | The Open for registration/Ongoing challenges should be sorted according to the option selected.
View More Challenges link (Before Login) | TC_019 | To verify whether the View more challenges link under the Open for registration/Ongoing Challenges list displays all the Open for registration/Ongoing challenges. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the View more Challenges link under the Open for registration list. | All the Open for registration challenges should be displayed.
[5 empty] | 3 | Click the View more Challenges link under the Ongoing Challenges list. | All the Ongoing challenges should be displayed.
Challenge tags functionality (Before login) | TC-020 | To verify that when user selects a challenge 'tag', only challenges under the selected tag are shown. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges | User should land on the challenge listings page
[5 empty] | 2 | Click on a challenge tag | Only challenges under the selected tag should be shown
Challenge count accuracy (Before login) | TC-021 | To verify that the challenge count matches the number of challenges displayed | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listings page
[5 empty] | 2 | Switch on/off the design, development and/or data science toggle buttons | The counts should change when switching the buttons
[5 empty] | 3 | Check the challenge count each time the buttons are turned on/off | The counts listed should match the number of challenges displayed on the page
Challenge count accuracy when returning back to listing page (Before login) | TC-022 | To verify that the challenge count remains the same when switching to the challenge details and then back to the challenge listings page | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" and observe the challenge count | User should land on the Challenge Listings page and challenge count should be displayed
[5 empty] | 2 | Click on any challenge | User should be directed to challenge details page
[5 empty] | 3 | Click on the back button. | User should be redirected to challenge listings page
[5 empty] | 4 | Observe the challenge count | Challenge count should remainto same as before
All Challenges Link Functionality With The Design, Development, and Data Science Toggle Switch On (Before login) | TC-023 | To verify All Challenges link functionality with the design, development, and data sceince toggle switches on |  |  | 1 | Go to given URL "https://www.topcoder.com/challenges" | User should land on the challenge page
[5 empty] | 2 | Click on the 'All Challenges' link | User should see a list of all development, design and data science challenges.
[5 empty] | 3 | Click on the 'Open for Registration' link | User should see a list of all development, design and data science challenges which are in 'open for registration' phase
[5 empty] | 4 | Click on 'Ongoing Challenges' link | User should see a list of all development, design and data science challenges which are not in 'open for registration' phase
[5 empty] | 5 | Click on the 'Open for Review' link | User should see a list of all development, design and data science challenges which need community review
[5 empty] | 6 | Click on the 'Past Challenges' link | User should see a list of all PAST development, design and data science challenges.
All Challenges Link Functionality With The Design, Development, and Data Science Toggle Switch off | TC-024 | To verify All Challenges link functionality with the design, development, and data sceince toggle switches Off |  |  | 1 | Go to given URL "https://www.topcoder.com/challenges"
[5 empty] | 2 | Make design, development, and data sceince toggle switches Off | Count of challege should be 0. All Challenges =0 My Challenges= 0 Open for registration= 0 Ongoing challenges = 0
[5 empty] | 3 | Click on the 'Open for Review' link | "There are no review opportunities available" message shold be disply on challenge section.
RSS Feed Link (Before Login) | TC_025 | To verify whether the page is redirected to the RSS Feed page on clicking the RSS feed link. | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the RSS Feed link. | The User should be redirected to the RSS Feed page.
link present under RSS Section (Before Login) | TC_026 | To verify whether the page is redirected to the respective page on clicking the link(About, Contact, Help, Privacy, Terms). | User should not be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the link(About, Contact, Help, Privacy, Terms) present under RSS Section | The User should be redirected to the respective page.
After Login Test Cases
Dashboard navigation (After Login) | TC_27 | To verify whether the current page is redirected to my Dashboard page on clicking the Dashboard under the Username menu. | User should be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Hover over the username displayed in top right corner. | All the sub menus Dashboard,My profile,Payments,Settings,Logout should be displayed.
[5 empty] | 3 | Click the Dashboard sub menu. | User should be redirected to the my Dashboard page.
My profile navigation (After Login) | TC_028 | To verify whether the current page is redirected to my profile page on clicking the my profile under the Username menu. | User should be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Hover over the username displayed in top right corner. | All the sub menus Dashboard,My profile,Payments,Settings,Logout should be displayed.
[5 empty] | 3 | Click the my profile sub menu. | User should be redirected to the my profile page.
Payment navigation (After Login) | TC_029 | To verify whether the current page is redirected to the payments page on clicking the payments under the Username menu. | User should be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Hover over the username displayed in top right corner. | All the sub menus Dashboard,My profile,Payments,Settings,Logout should be displayed.
[5 empty] | 3 | Click the payments sub menu. | User should be redirected to the payments page.
Settings navigation (After Login) | TC_030 | To verify whether the current page is redirected to the settings page on clicking the settings under the Username menu. | User should be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Hover over the username displayed in top right corner. | All the sub menus Dashboard,My profile,Payments,Settings,Logout should be displayed.
[5 empty] | 3 | Click the settings sub menu. | User should be redirected to the settings page.
Logout Function (After Login) | TC_031 | To verify whether the logout happens on clicking the logout under the Username menu. | User should be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Hover over the username displayed in top right corner. | All the sub menus Dashboard,My profile,Payments,Settings,Logout should be displayed.
[5 empty] | 3 | Click the logout sub menu. | The user should be logged out of topcoder.
Member Search Function (After Login) | TC_032 | To verify whether the user is able to search the member by their username/skill using the search icon. | User should be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the search icon into top right corner. | Find members textbox should be opened.
[5 empty] | 3 | Type a valid username and click search icon into textbox. | Members with the entered username should be listed.
|  |  |  | Java,QA,Azure etc | 4 | Type a valid skill and click search icon into textbox. | Members with the entered skill should be listed.
Challenge tab (After Login) | TC_033 | To verify whether all the my challenges,open for registration and Ongoing challenges are listed on clicking the Challenge tab. | User should be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click the Challenge tab. | All the my challenges,open for registration and Ongoing challenges should be listed.
SRM tab (After Login) | TC_034 | To verify whether the Topcoder arena page is opened on clicking the SRM tab. | User should be logged in |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the Challenge Listing page.
[5 empty] | 2 | Click on 'Ongoing Challenges' link | User should see a list of all design and data science challenges which are Not in 'Open for registration' phase. User should not see any development challenges.
[5 empty] | 2 | Click on the 'All Challenges' link | User should see a list of all design challenges. User should not see development and data science challenges.

## Challenge Details
Case Name | Case Number | Description | Preconditions | Test Data | Steps to Execute Test Case |  | Expected Result | Actual Result | Status
[5 empty] | Steps Number | Steps
Back button funtionality | TC-001 | To verify that back button redirects user to challenge listings page when selected | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/challenges" | User should land on the challenge listings page
[5 empty] | 2 | Click on any of the challenges listed | User should be directed to a challenge specification page
[5 empty] | 3 | Click on the back button situated to the left of the page title | User should be redirected to the Challenge listings
Submission process | TC-002 | To verify that a user is able to successfully enter a submission to a code challenge | User should be logged in and registered for the challenge |  | 1 | Go to the given URL " https://www.topcoder.com/challenges/30102280" | User should land on a challenge details page
[5 empty] | 2 | Click on the "Submit" button | User should be directed to submission page
[5 empty] | 3 | Drag and drop a zip file or click on the "Pick a file" button to attach a submission in .zip format | Submission in .zip file format should be attached
[5 empty] | 4 | Check the box for "I UNDERSTAND AND AGREE" and click "Submit" | Submission should be successfully uploaded
Challenge Details(Before Login) | TC_003 | To verify whether the error message is displayed on clicking the Challenge Terms link. | User should not loginto Topcoder. |  | 1 | Go to given URL ' https://www.topcoder.com/challenges/30102280' | User should land on the particular Challenge details page.
[5 empty] | 2 | Click the Challenge Terms link. | The error message "Authentication credentials was missing" should be displayed
Challenge Details(After Login) | TC_004 | To verify whether the user is registered to the particular challenge on clicking the Register button. | User should be logged into Topcoder. |  | 1 | Go to given URL ' https://www.topcoder.com/challenges/30102280' | User should land on the particular Challenge details page.
[5 empty] | 2 | Click the Register button. | 1.User should be registered to the particular challenge and button name should be changed to UnRegister 2. Challenge forum tab will occurr.
[5 empty] | 3 | Click the Challenge Forum tab. | The user should be redirected to the particular Challenge forum page
Challenge Details(After Login) | TC_005 | To verify whether the user is unregistered into particular challenge on clicking the UnRegister button. | User should be logged into Topcoder. |  | 1 | Go to given URL ' https://www.topcoder.com/challenges/30102280' | User should land on the particular Challenge details page.
[5 empty] | 2 | Click the Register button. | User should be registered to the particular challenge and button name should be changed to UnRegister.
[5 empty] | 3 | Click the UnRegister button. | User should be unregistered into particular challenge and button name should be changed to Register.
Challenge Details(After Login) | TC_006 | To verify whether the user is redirected to the Submission page on clicking the Submit button. | User should be logged into Topcoder. |  | 1 | Go to given URL ' https://www.topcoder.com/challenges/30102280' | User should land on the particular Challenge details page.
[5 empty] | 2 | Click the Submit button. | The user should be redirected to the Submission page.
Challenge Details(After Login) | TC_007 | To verify whether the deadlines(time zone) for the particular challenge on clicking the show Deadlines. | User should be logged into Topcoder. |  | 1 | Go to given URL ' https://www.topcoder.com/challenges/30102280' | User should land on the particular Challenge details page.
[5 empty] | 2 | Click the Show Deadlines. | All the deadlines(time zone) for the Started,Registration,Submission,Review,Winners etc will be shown. And button text will change as Hide Deadlines.
[5 empty] | 3 | Click on Hide Deadlines | Panel will collaps.
Challenge Details(After Login) | TC_008 | To verify whether the details of the challenges are displayed on clicking the Details tab. | User should be logged into Topcoder. |  | 1 | Go to given URL ' https://www.topcoder.com/challenges/30102280' | User should land on the particular Challenge details page.
[5 empty] | 2 | Click the Details tab. | The details of the challenges should be displayed
Challenge Details(After Login) | TC_009 | To verify whether the registered members of the challenges are displayed on clicking the Registrants tab. | User should be logged into Topcoder. |  | 1 | Go to given URL ' https://www.topcoder.com/challenges/30102280' | User should land on the particular Challenge details page.
[5 empty] | 2 | Click the Registrants tab. | The registered members of the challenges should be displayed
Challenge Details(After Login) | TC_010 | To verify whether the Solution submitted members are displayed on clicking the Submissions tab. | User should be logged into Topcoder. |  | 1 | Go to given URL ' https://www.topcoder.com/challenges/30102280' | User should land on the particular Challenge details page.
[5 empty] | 2 | Click the Submissions tab. | The Solution submitted members of the challenges should be displayed | Submission tab only display if any user has submitted the deliverable.
Challenge Details(After Login) | TC_011 | To verify whether the user is redirected to the Review Scorecard page on clicking the Review Scorecard link. | User should be logged into Topcoder. |  | 1 | Go to given URL ' https://www.topcoder.com/challenges/30102280' | User should land on the particular Challenge details page.
[5 empty] | 2 | Click the Review Scorecard link. | The user should be redirected to the Review Scorecard page
Challenge Details(After Login) | TC_012 | To verify whether the user is redirected to the Challenge Terms page on clicking the Challenge Terms link. | User should be logged into Topcoder. |  | 1 | Go to given URL ' https://www.topcoder.com/challenges/30102280' | User should land on the particular Challenge details page.
[5 empty] | 2 | Click the Challenge Terms link. | The user should be redirected to the Challenge Terms page

## Dashboard
Case Name | Case Number | Description | Preconditions | Test Data | Steps to Execute Test Case |  | Expected Result | Actual Result | Status
[5 empty] | Steps Number | Steps
Dashboard Availability (After login) | TC-001 | To verify that user is able to view dashboard when logged in. | User should be logged in. |  | 1 | Go to the given URL " https://www.topcoder.com/my-dashboard" | User's dashboard should be displayed
Dashboard Availability (Before login) | TC-002 | To verify that user is redirected to login page when logged out and attempting to access dashboard page | User should be logged out. |  | 1 | Go to the given URL " https://www.topcoder.com/my-dashboard" | User should be directed to the login page